## Sheet1
Project | Defect ID | Summary | Detected on Date | Detected By | SW Revision & Build | GI Development | Issue Type | Priority | Classification | DRB Reviewed | Reproducible | Status | Assigned To | Target Cycle | External Defect ID | Verifier | Disposition | Root Cause | Duplicate ID | Resolved By | Resolved in Branch or Version | Resolve Date | Verify Date | Category | Status Update | DRB Comments | Comments | T2/Common? | Triage
Osprey R4 | 92734 | The system has to keep PA mode after pressing freeze button,but the system switches to Scan on Battery mode. | 2023-06-02 | minjae.kweon | R4.5.3C | N | Functionality Bug | 2-Medium | NC - Design Non-Conformance | Y | Y | Closed | doo je.sung |  |  | minjae.kweon | Documentation Change | Test requirements/execution |  | doo je.sung | Documents | 2023-06-26 | 2023-06-30 | Other | ME2_2023FW25 R4.5.3 | <Osprey R4 DRB Review Result> ====================================================================== Defect Review Board date : 2023-Jul-12 ~ 2023-Jul-12 Attendee : Kyohoon Baek (LSD), Wook Jang(QA), Hanil Lee (SW Engineer), Maria Kim Eunhee (Clinical mkt), Engineering team --------------------------------------------------------- Report Assessment (NOTE: Question 1 MUST be answered): --------------------------------------------------------- 1) Is there a potential Safety Concern? (Y/N) : N 2) Nonconformance to a Design Requirement? 2-1) Known Systemic Design Flaw that impairs the intended use or user needs of the device? (Y/N) : N 2-2) Reliability requirement, Data Sheet, Product Labeling, Promotional Claim that applies? (Y/N) : N 2-3) Nonconformance to Regulatory Requirements in a region intended for sale? (Y/N) : Y 3) Error in Verification/Validation Test Cases? If yes, specify DOC# and test ID (Y/N) : N --------------------------------------------------------- Assessment Result (Hazardous/Design NC / IO) : NC --------------------------------------------------------- Other products affected : N/A --------------------------------------------------------- Significance Level (Critical/Major/Minor) : ###MINOR### --------------------------------------------------------- Significance Rationale IB impact : No impact. Patient safety : No impact. Patient diagnosis : No impact. Hazardous situation lead : No. This is verification test procedure Document issue and not related to any of system functionality or performance. --------------------------------------------------------- Frequency / Probability (Likely/Occasional/Rare) : Likely --------------------------------------------------------- Frequency / Probability Rationale It will continue to happen until the document is updated. --------------------------------------------------------- Impact Level (High/Medium/Low) : ###LOW### ======================================================================